## Technology stack
Component | Framework/Tool
RESTful services | ASP.NET Core Web API
Database | SQL Azure
ORM | Entity Framework Core OR Dapper
Dependency Injection | SimpleInjector
Transaction Management | .Net TransactionScope
Logging | NLog
API Unit testing | VS Testing tools(MSTest) OR NUnit
API Mocking | Fakes OR Moq
API Static code analysis | SonarLint
API Documentation | Swagger
Client UI | Angular 6, HTML5, CSS3, Bootstrap
UI Unit testing | Jasmine and Karma
UI Static code analysis | TSLint
Authentication | Azure AD
File Storage | Azure blobs

## Technical stories
Description | Acceptance criteria | Status | Owner | Start Date | End Date | Efforts
Version control | 1. Setting up of GitLab repository and branches | Done | Yashaswini
CI/CD | 1. Setting up of CI/CD pipeline in Jenkins |  | Yashaswini | 2018-08-17
API
Solution/Project Structure | 1. Identify of all project/class libraries required for the project 2. Create projects with appropriate namespace | Done | Shuvam, Shubra | 2018-08-17
Domain Model | 1. Create the DB schema 2. Upload DDL and sample data insertion scripts to GitLab 3. Migration strategy |  | Siddharth, Hemasai | 2018-08-17
DAL - Framework to access persistence storage | 1. Set up ORM using either Entity Framework or Dapper 2. Wrapper class with generic data access method |  | Yashaswini | 2018-08-18
Exception handling strategy for API | 1. Sample code showcasing the exception flow across the tiers 2. Define error code for different modules and scenarios |  | Yashaswini | 2018-08-18
Service decomposition | 1. Identify required API endpoints with RESTful routes 2. Create controllers |  | Siddharth, Hemasai | 2018-08-17
Logging framework using Nlog | 1. Configure Nlog to write logs to a text file | Done | Shuvam, Shubra | 2018-08-17
Transaction management | 1. Sample code to demonstrate usage of TransactionScope | Done | Aryashree | 2018-08-17
Dependency injection | 1. Configure SimpleInjector to support DI | Done | Shuvam, Shubra | 2018-08-17
Authentication strategy | 1. Steps to configure AD authentication in API |  | Charan | 2018-08-17
Authorization framework
Swagger configuration | 1. Setup Swagger using Swashbuckle |  | Siddharth, Hemasai | 2018-08-17
Upload / Download framework in API | 1. Zip file extraction 2. Read the contents of excel files inside it into a List/DataTable |  | Mayank | 2018-08-17
Azure blob services | 1. Create storage account in Azure 2. Create AzureBlobManager class to upload and download files from blob |  | Charan | 2018-08-18
Email notification component | 1. EmailManager to send email for different scenarios in the application 2. EmailHelper to handle the logistics of sending email like configuration of SMTP server etc.
UI
Wireframes | 1. Complete wireframes covering all the features of the user stories |  | Shuvam, Shubra | 2018-08-18
Code structure | 1. Identify components, modules, services, routing required based on the wireframes 2. Setup project structure using Angular CLI |  | Jagat, Mayank | 2018-08-20
Exception handling framework for UI using ErrorHandler |  |  | Aryashree | 2018-08-17
Authentication strategy | 1. Setup AD authentication using msal.js |  | Charan | 2018-08-17
Authorization framework
Wrapper for HttpClient |  |  | Hemasai
Minification and bundling |  | Done | Aryashree | 2018-08-17
Generic Upload / Download component in UI |  |  | Jagat, Mayank | 2018-08-17